Eco Schools Action Plan 2025-26
Action Plan was developed: November 2025
Topic	Action	Target/Measure	Timescale/ / Deadline	Responsibility	Evaluation of action/actual result achieved
Eco Schools	To create a school Eco Policy.	To deliver a clear rationale about our schools aims and future development for being a successful and sustainable Eco School	Dec 2026	Mrs Lennon, / Mr Ruffles and Eco Ambassadors
	To update the profile of Eco Schools on the school website and newsletter.	To enable all school website visitors and all our school community to read about current Eco School activities.	Feb 2026	Mr Ruffles, Mrs Lennon and Justine
	To create a school eco-code.	To work with the whole school community to create an eco-code – Class competition	July 2026	Whole school community
Water	Class based assemblies to raise awareness of water issues and discuss how we can help.	To raise children’s awareness of people in the world who do not have access to clean water.	Jan 26	Class Teachers and Eco Team.
	Install a water butt on the school playground to use to water the plants around school.	To reduce the amount of water wasted at school.	July 2026	Mr Mace, Mr Ruffles, Mrs Lennon and Eco Team.
	Change the taps in the sinks opposite class 3C to self closing taps.	To reduce the amount of water wasted at school.	July 2026	SLT, Mr Mace
School Grounds and Biodiversity	New habitats created e.g. bug hotels, plant flowers rich in pollen and create wildflower area.	To encourage wildlife by creating habitats in the science garden / (bugs, butterflies and bees).	May 26	Parents, volunteers, Eco Team, Mr Mace, Mr Ruffles, Mrs Douglas and Mrs Lennon
	To create an allotment area and sow and plant a variety of vegetables.	To grow and eat food grown in the allotment.	July 26	SLT, Parents, volunteers, Eco Team, Mr Mace, Mr Ruffles, Mrs Douglas, Mrs Lennon and Mrs Palmer
Litter/Waste	Eco Ambassadors to pick up litter using litter pickers.	Reduce litter in the school grounds and the perimeter footpaths.	Feb 26	Eco Ambassadors, Mr Ruffles, Mrs Lennon and Mrs Douglas.
	Class based on waste reduction.	Increase awareness of and limit waste in and around school.	Dec 2026	Class Teachers and Eco Ambassadors.
	Enhance school wide recycling. Every class to have a recycling bin. / Emptied regularly.	To increase the amount of paper/card we recycling and reduce waste.	Mar 2026	Whole school