| Eco-Schools Topic 1 Biodiversity | Action(s): - Approach the headteacher to find out if we are able to claim part of the field. - Draw up plans for the area. - Cost resources: Grass seeds Wild flower seeds Fencing - Arrange a working party to develop the area. - Apply for a tree pack from the Forestry Commission. - Plant the young trees. | How long will it take? To be completed by the start of the summer term. | How will we monitor progress? Updates will be given at each eco meeting. Once completed weekly checks to identify if we have any signs of wildlife in the area. Weekly check on trees to ensure they are growing. |
| --- | --- | --- | --- |
| Aim: To develop a wildflower / meadow area on the school field. Plant a range of young trees in the school field. |  | Who is responsible? Eco Committee to talk to headteacher. Eco committee, AS & SM to design the area. AS & SM to price up resources. Eco Committee to send out request for help to parents. AS to apply for trees. AS and Eco Committee to plan the trees. | Evaluation: |
| Eco-Schools Topic 2 Litter | Action(s): - Purchase litter picking equipment. - Take part in Keep Britain Tidy’s Great Big School Clean 2022. - Arrange a rota for children to collect litter around the school grounds at lunch time. | How long will it take? The Keep Britain Tidy’s Great Big School Clean to take place in April. Litter picking around school to continue weekly. | How will we monitor progress? By checking the amount of litter collected during each session. A reduction in the amount of litter will show progress. |
| Aim: To reduce the amount of litter in our local area. |  | Who is responsible? AS to purchase litter pickers. AS to enrol school on the Big School Clean. Eco Committee to use equipment to collect the litter from around school. | Evaluation: |
| Eco-Schools Topic 3 Energy | Action(s): - Make posters to remind everyone to turn off lights when they leave the room. - Ensure each classroom has a monitor to ensure the projectors are turned off when not needed. - To take part in an energy switch off in school during the summer term. | How long will it take? Posters to be completed within 2 weeks. Ongoing reminders about saving energy. | How will we monitor progress? We will ask for weekly meter readings through the summer term to monitor the amount of energy used. |
| Aim: To reduce the amount of energy wasted during the school day. |  | Who is responsible? Eco committee to approach the headteacher to arrange energy switch off. Eco committee to produce posters. | Evaluation: |

Ot